## Features
Phase | Feature | Description
0 | Security | SuperAdmin Login /Signup
1 | Permission | SuperAdmin creates Permissions

## Feature Tracker
FEATURE TRACKER – LAW ERP
# | Phase | Module | Feature Name | Description | PATH | Overall Status | Backend | Frontend | Testing | Target Date | Notes
───────────────────────────────────────────────────── PHASE 0 Super Admin Login ────────────────────────────────────────────────────────-──────────────────────────────────────────
1 | Phase 0 | Security | Signup | Signup Using a key only from POSTMAN | api/v1/super-admin/register | IN PROGRESS | Completed | Completed
2 |  |  | SignIn SuperAdmin | Sign In normall | /api/v1/super-admin/login | IN PROGRESS | Completed | Completed
3 |  |  | Login | Login for all users | /api/v1/login |  | Completed |  |  |  | FIrm COde for firm and employee and clients
4
5
6
7
8
───────────────────────────────────────────────────── PHASE 1 Permission Management────────────────────────────────────────────────────-──────────────────────────────────────────
9 | Phase 1 | Permission | Permission CRUDE | Create / Update Permission | /api/v1/admin/permissions {POST} | IN PROGRESS | Completed | Completed
10 |  |  | Permission CRUDE | Get Permissions | /api/v1/admin/permissions {GET} | IN PROGRESS | Completed | Completed
11 |  |  | Permission CRUDE | Get All Active Permissions | /api/v1/admin/permissions/active |  | Completed | Completed
12 |  |  | Permission CRUDE | Get By ID | /api/v1/admin/permissions/{id} {GET} |  | Completed | Completed
13 |  |  | Permission CRUDE | Delete By Id | /api/v1/admin/permissions/{id} {DELETE} |  | Completed | Completed
14 |  |  | Permission CRUDE | Toggle Status of Permission | /api/v1/admin/permissions/{id}/toggle |  | Completed | NOT STARTED
15 | Phase 2 | Role | Role CRUD | Create / Update Role | /api/v1/admin/roles {POST} |  | Completed | Completed
16 | Phase 2 | Role | Role CRUD | Get All Roles | /api/v1/admin/roles {GET} |  | Completed | Completed
17 | Phase 2 | Role | Role CRUD | Get Active Roles | /api/v1/admin/roles/active {GET} |  | Completed
18 | Phase 2 | Role | Role CRUD | Get Role By ID | /api/v1/admin/roles/{roleId} {GET} |  | Completed | Completed
19 | Phase 2 | Role | Role CRUD | Delete Role By ID | /api/v1/admin/roles/{roleId} {DELETE} |  | Completed
20 | Phase 2 | Role | Role CRUD | Toggle Role Status | /api/v1/admin/roles/{roleId}/toggle {PATCH} |  | Completed | Completed
21 | Phase 3 | Role-Permission | Role Permission Mapping | Assign Permissions to Role | /api/v1/admin/roles/permissions {POST} |  | Completed | Completed
22 | Phase 3 | Role-Permission | Role Permission Mapping | Get Role Permissions | /api/v1/admin/roles/{roleId}/permissions {GET} |  | Completed | Completed
23 | Phase 4 | Module | Module CRUD | Create / Update Module | /api/v1/admin/modules {POST} |  | Completed | Completed |  |  | If parentId is sent it makes it subModule,Make the api to take Icons too [MultiPart File]
24 | Phase 4 | Module | Module CRUD | Get All Modules (Tree) | /api/v1/admin/modules {GET} |  | Completed | Completed
25 | Phase 4 | Module | Module CRUD | Get Active Modules (Tree) | /api/v1/admin/modules/active {GET} |  | Completed
26 | Phase 4 | Module | Module CRUD | Get Flat Modules List | /api/v1/admin/modules/flat {GET} |  | Completed
27 | Phase 4 | Module | Module CRUD | Get Module By ID | /api/v1/admin/modules/{moduleId} {GET} |  | Completed | Completed
28 | Phase 4 | Module | Module CRUD | Delete Module By ID | /api/v1/admin/modules/{moduleId} {DELETE} |  | Completed | NOT STARTED
29 | Phase 4 | Module | Module CRUD | Toggle Module Status | /api/v1/admin/modules/{moduleId}/toggle {PATCH} |  | Completed
───────────────────────────────────────────────────── PHASE 5 Employee Management────────────────────────────────────────────────────-──────────────────────────────────────────
30 | Phase 5 | Employee | Employee CRUD | Create Employee | /api/v1/firm/employees {POST} |  | Completed | Completed
31 | Phase 5 | Employee | Employee CRUD | Get All Employees | /api/v1/firm/employees {GET} |  | Completed | Completed
32 | Phase 5 | Employee | Employee CRUD | Get Employee By ID | /api/v1/firm/employees/{employeeId} {GET} |  | Completed | Completed
33 | Phase 5 | Employee | Employee CRUD | Update Employee | /api/v1/firm/employees/{employeeId} {PUT} |  | Completed
34 | Phase 5 | Employee | Employee CRUD | Update Employee Role | /api/v1/firm/employees/{employeeId}/role {PATCH} |  | Completed
35 | Phase 5 | Employee | Employee CRUD | Toggle Employee Status | /api/v1/firm/employees/{employeeId}/toggle {PATCH} |  | Completed
───────────────────────────────────────────────────── PHASE 6 Client Management────────────────────────────────────────────────────-──────────────────────────────────────────
36 | Phase 6 | Client | Client CRUD | Create Client | /api/v1/firm/clients {POST} |  | Completed | Completed
37 | Phase 6 | Client | Client CRUD | Get All Clients | /api/v1/firm/clients {GET} |  | Completed | Completed
38 | Phase 6 | Client | Client CRUD | Get Client By ID | /api/v1/firm/clients/{clientId} {GET} |  | Completed | Completed
39 | Phase 6 | Client | Client CRUD | Toggle Client Portal Access | /api/v1/firm/clients/{clientId}/portal-access {PATCH} |  | Completed | Completed
───────────────────────────────────────────────────── PHASE 7 FIRM ROLE Management────────────────────────────────────────────────────-──────────────────────────────────────────
40 | Phase 7 | Firm Role | Firm Role View | Get Firm Roles (Dropdown) | /api/v1/firm/roles {GET} |  | Completed | Completed
41 | Phase 12 | Firm Role | Firm Role Management | Get Role Permissions | /api/v1/firm/roles/{roleId}/permissions {GET} |  | Completed
42 | Phase 12 | Firm Role | Firm Role Management | Update Role Permissions | /api/v1/firm/roles/{roleId}/permissions {PUT} |  | Completed |  |  |  | DIscuss garna parcha eslai
───────────────────────────────────────────────────── PHASE 8 Audit Logs Management────────────────────────────────────────────────────-──────────────────────────────────────────
43 | Phase 8 | Audit | Audit Logs | Get Firm Audit Timeline | /api/v1/firm/audit {GET} |  | Completed
44 | Phase 8 | Audit | Audit Logs | Get User Audit Timeline | /api/v1/firm/audit/users/{userId} {GET} |  | Completed
45 | Phase 8 | Audit | Audit Logs | Get Entity History | /api/v1/firm/audit/entities/{entityType}/{entityId} {GET} |  | Completed
46 | Phase 8 | Audit | Audit Logs | Filter Audit by Action | /api/v1/firm/audit/actions {GET} |  | Completed
47 | Phase 8 | Audit | Audit Logs | Get Firm Audit (Super Admin) | /api/v1/super-admin/audit/firms/{firmId} {GET} |  | Completed | Completed
48 | Phase 8 | Audit | Audit Logs | Get Global Action Audit | /api/v1/super-admin/audit/actions {GET} |  | Completed
───────────────────────────────────────────────────── PHASE 9 USER Management────────────────────────────────────────────────────-──────────────────────────────────────────
49 | Phase 9 | User Management | User | List All Users | /api/v1/modules/users {GET} |  | Completed
50 | Phase 9 | User Management | User | Search Users | /api/v1/modules/users/search {GET} |  | Completed
51 | Phase 9 | User Management | User | Get User Profile | /api/v1/modules/users/{userId}/profile {GET} |  | Completed
52 | Phase 9 | User Management | User | Get User Permissions | /api/v1/modules/users/{userId}/permissions {GET} |  | Completed
53 | Phase 9 | User Management | User | Get User Activity | /api/v1/modules/users/{userId}/activity {GET} |  | Completed
54 | Phase 9 | User Management | User | Reset User Password | /api/v1/modules/users/{userId}/reset-password {POST} |  | Completed
55 | Phase 9 | User Management | User | Bulk Deactivate | /api/v1/modules/users/bulk-deactivate {POST} |  | Completed
56 | Phase 9 | User Management | User | Bulk Role Change | /api/v1/modules/users/bulk-role-change {POST} |  | Completed
57 | Phase 9 | User Management | Employee | Create employees | api/v1/firm/employees {POST} |  | Completed
58 | Phase 9 | User Management | Employee | Get All employeess | /api/v1/firm/employeess {GET} |  | Completed
59 | Phase 9 | User Management | Employee | Get employees By ID | /api/v1/firm/employeess/{employeesId} {GET} |  | Completed
60 | Phase 9 | User Management | Employee | Update employees | /api/v1/firm/employeess/{employeeId} {PUT} |  | Completed
61 | Phase 9 | User Management | Employee | Delete employees | /api/v1/firm/employeess/{employeeId} {DELETE} |  | Completed
62 | Phase 11 | Firm Module | Firm Module | Enable/Disable Module | /api/v1/super-admin/firms/{firmId}/modules {POST} |  | Completed
63 | Phase 11 | Firm Module | Firm Module | Get Firm Modules | /api/v1/super-admin/firms/{firmId}/modules {GET} |  | Completed
64 | Phase 11 | Firm Module | Firm Module | Get My Enabled Modules | /api/v1/firm/modules {GET} |  | Completed
65 | Phase 11 | Me | Me Module | Me APi | /api/v1/me |  | Completed
66
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112 | Phase 13 | System Config | Global Config CRUD | Set platform SMTP, app name, production flag (Super Admin) | /api/v1/super-admin/config {PUT} |  | Completed |  |  |  | Bulk upsert. SMTP_PASSWORD AES-encrypted.
113 |  |  |  | Get all global config values | /api/v1/super-admin/config {GET} |  | Completed |  |  |  | Returns decrypted map of all GLOBAL keys
114 |  |  |  | Delete a global config key | /api/v1/super-admin/config/{key} {DELETE} |  | Completed
115 |  |  |  | Set per-firm brand config (Super Admin) | /api/v1/super-admin/firms/{id}/config {PUT} |  | Completed |  |  |  | Brand colors, email footer, timezone
116 |  |  |  | Get per-firm brand config | /api/v1/super-admin/firms/{id}/config {GET} |  | Completed
117 |  |  |  | Firm admin reads/updates own brand config | /api/v1/firm/config {GET / PUT} |  | Completed |  |  |  | Brand colors, footer, timezone, signature
118 | Phase 13 | Email Config | Firm Email Config CRUD | Get firm email SMTP config | /api/v1/firm/email-config {GET} |  | Completed |  |  |  | Password returned as smtpPasswordSet: bool
119 |  |  |  | Create/update firm SMTP config | /api/v1/firm/email-config {PUT} |  | Completed |  |  |  | __UNCHANGED__ sentinel keeps password intact
120 |  |  |  | Delete firm email config (reset to platform fallback) | /api/v1/firm/email-config {DELETE} |  | Completed
121 |  |  |  | Test SMTP connection | /api/v1/firm/email-config/test {POST} |  | Completed |  |  |  | Tests connection, saves testPassed + testedAt
122 | Phase 13 | Email | Async Email Sending | Welcome email to new employee | EmailService.sendWelcomeEmployee() |  | Completed |  |  |  | Triggered on POST /firm/employees. HTML template with firm brand colors.
123 |  |  |  | Welcome email to new client | EmailService.sendWelcomeClient() |  | Completed |  |  |  | Triggered on POST /firm/clients
124 |  |  |  | Welcome email to firm admin | EmailService.sendWelcomeFirmAdmin() |  | Completed |  |  |  | Triggered on firm creation by Super Admin
125 |  |  |  | Password reset email | EmailService.sendPasswordReset() |  | Completed |  |  |  | Triggered on POST /modules/users/{id}/reset-password
126 | Phase 13 | Email | HTML Email Templates | Employee welcome template | src/main/resources/templates/email/welcome-employee.html |  | Completed |  |  |  | Thymeleaf with firm brand color injection
127 |  |  |  | Client welcome template | src/main/resources/templates/email/welcome-client.html |  | Completed
128 |  |  |  | Firm admin welcome template | src/main/resources/templates/email/welcome-firm-admin.html |  | Completed
129 |  |  |  | Password reset template | src/main/resources/templates/email/password-reset.html |  | Completed
130 | Phase 13 | Infra | @Async + ThreadPool | Enable async email + audit with thread pool | BeanConfig.java + SecurityConfig.java |  | Completed |  |  |  | @EnableAsync + ThreadPoolTaskExecutor (core=2, max=5)
131 |  |  |  | Separate async audit writer bean | AsyncAuditWriter.java |  | Completed |  |  |  | Fixes self-invocation proxy bypass
132 |  |  |  | AES-256 GCM config encryption | ConfigEncryptionUtil.java |  | Completed |  |  |  | Encrypts SMTP_PASSWORD in system_config + firm_email_configs
133 | Phase 13 | Docs | Postman Collection | Full collection for email + config testing | NepalCRM-Email-Config-API.postman_collection.json |  | Completed |  |  |  | 8 folders, ~30 requests, auto-captures tokens
134 | Phase 11 | Me | Me API added brand config | GET /me now returns brandColorPrimary, brandColorSecondary, appName | /api/v1/me {GET} |  | Completed |  |  |  | Reads from system_config FIRM scope
135 | Phase 5 | Employee | Role assignment fix | Allow system roles with applicableTo=FIRM_USER for old firms without clones | /api/v1/firm/employees {POST} |  | Completed |  |  |  | Fixed validateFirmRole() + getFirmRoles() fallback

## BUGs Fixes
FEATURE TRACKER – LAW ERP
# | Module | Feature Name | Description | PATH | Overall Status | BUG In | SOLVED | Notes
1 | Security | Signup | Signup Using a key only from POSTMAN | api/v1/super-admin/register | NOT STARTED |  | FALSE
2 |  | Pagination | Add paginations for get apis | admin/roles | NOT STARTED | BackEnd | FALSE
3 |  |  | Cannot update employee data without providing the password field. | /api/v1/firm/employees/{employeeId} | NOT STARTED | BackEnd | FALSE
4 |  |  | Modules and permissions assigned through the POST API are not reflected in GET API response | /admin/roles | NOT STARTED | BackEnd | FALSE
[5 empty] | NOT STARTED |  | FALSE
[5 empty] | NOT STARTED |  | FALSE
[5 empty] | NOT STARTED |  | FALSE
[5 empty] | NOT STARTED |  | FALSE
[5 empty] | NOT STARTED |  | FALSE
[5 empty] | NOT STARTED |  | FALSE